## Project Planner
FYP Timeline |  |  |  |  | Period Highlight: |  |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Initial Background Reading | 3 | 1 | 3 | 1 | 100%
Inception Report | 4 | 1 | 4 | 1 | 100%
JPEG2000 | 4 | 1 | 4 | 1 | 100%
kNN, K-means, Dictionary Learning, Sparse Coding | 5 | 2 | 5 | 2 | 100%
FRESH | 7 | 2 | 7 | 2 | 100%
UFRESH | 8 | 2 | 8 | 2 | 100%
Autumn Term Coursework Deadlines | 9 | 3 | 9 | 3 | 100%
Control Engineering Exam Preparation | 10 | 2 | 10 | 2 | 100%
Christmas Break | 12 | 3 | 12 | 3 | 100%
Managerial Economics Exam Preparation | 14 | 1 | 14 | 1 | 100%
Anchored Neighbourhood Regression(ANR) | 15 | 1 | 15 | 1 | 100%
Convolutional Neural Networks(CNN) | 15 | 1 | 15 | 1 | 100%
Current State-of-the-art | 15 | 3 | 15 | 3 | 100%
Interim Report | 17 | 1 | 17 | 1 | 100%
Further Literature Review | 18 | 2 | 18 | 2 | 0%
Analysis of Relative Merits of Each Technique | 20 | 1 | 20 | 1 | 0%
Combining Existing Methods | 21 | 3 | 21 | 3 | 0%
Testing and analysis | 22 | 2 | 22 | 2 | 0%
Analysis of Current Minimization Problem | 23 | 2 | 23 | 2 | 0%
Spring Term Coursework Deadlines | 25 | 2 | 25 | 2 | 0%
Designing Improvements | 27 | 3 | 27 | 3 | 0%
Testing and Analysis | 28 | 3 | 28 | 3 | 0%
Contingency Period | 31 | 2 | 31 | 2 | 0%
Final Report | 33 | 4 | 33 | 4 | 0%
Presentation | 37 | 2 | 37 | 2 | 0%